## Problems
ID | Section | Problem | What to do | Done when | Contribution | Phase | Priority | Difficulty (1-5) | Est. weeks | Depends on (IDs) | Status | Notes
1 | A. Foundations | Verify the curvature claim | Re-derive that the per-event loss l_i(θ) = −log(a_iᵀθ) + b_iᵀθ has a rank-one Hessian and is not exp-concave when b_i is not parallel to a_i. Then find the correct curvature statement: look at the expected loss, whose Hessian is the Fisher information per unit time, and bound its smallest eigenvalue on Θ_ε = {μ ≥ μ_min, α ≥ 0, n ≤ 1−ε}. | A short written lemma with the counterexample, plus the corrected curvature statement and a bound on the smallest eigenvalue. | C1 | P1 Core feasibility | Critical | 3 | 1 |  | Done | Draft done 2026-10-24. Hessian a a^T/lam^2 is rank one; exp-concavity fails whenever b not parallel to a (counterexample checked numerically). Corrected statement: expected-loss Hessian >= c(theta)^-2 I(theta*), and lam_min(I) >= (eps/mu)*inf_v(E¦v^T a¦)^2 by Cauchy-Schwarz; K=1 exact check gives lam_min ~ eps/mu. Needs your own re-derivation. Open: alpha*_k=0 case, stationarity/burn-in. See problem01_curvature_lemma.md
2 | A. Foundations | Identifiability of the dictionary | On a fixed β-grid, decide whether the weights α are identifiable, i.e. whether the Fisher information I(θ) is nonsingular. Nearby β_k make the exponentials almost collinear, so the condition number grows with K and with grid density. Quantify it. | An explicit lower bound on λ_min(I(θ)), or on the condition number, in terms of K and the grid ratio. | C1 | P2 Complete upper bound | High | 3 | 1.5 | 1 | Done | 25 Oct 2026. problem02_identifiability.md; code/p2_window_bound.py, p2_lemma3_check.py, p2_gram_bound.py, p2_truncation_check.py, p2_truncation_bound.py. Fixed a thinning bug in p2_identifiability.py (had made lam_min ~10x too small for K>=2). Findings (mu=1, beta=r^(k-1), MC 60-80k events): K>=2 lam_min does NOT shrink with eps (K=2: ~0.045 at r=2, ~0.065 at r=4), cond ~ 1/eps (K=1: eps^-2); lam_min falls ~10x per added exponential (r=2: 0.069, 0.046, 0.0045 for K=1,2,3 at eps=0.1). Lower bounds: (1) Gram-matrix route is rigorous but useless (1e-6 to 1e-16 of truth, decays like eps^(2K+1)). (2) Theorem T (truncation + Lemma-B moments): lam_min(I) >= (1/L)[lam_min(M) - sqrt(E¦a¦^4) sqrt(E lam^p / L^p)], M = E[a a^T] exact via a K^2 linear system (matches MC to 1-3%); bound is 2e-3 to 5e-2 of the MC lam_min for K<=3 and non-vacuous; pure truncation without tail penalty would be within 2-8x. Open: closed-form formula in K and grid ratio, sharper tail bound, eps-sharpness for K>=2. Depends on Lemma B (Problem 3 draft). Draft, not independently verified. CLOSED 25 Oct (Done): closed-form chain in K and grid ratio r: Cov(S) >= (E lam/4) G (G=1/(b_i+b_j), spectral), exact E S_k = mu/(eps b_k), lam_min(M) >= lam_min(C)/(1+2¦m¦^2), Cauchy inverse in closed form, then truncation with Lemma-1' moments; valid but 1e3-1e8 below truth (code/p2_closed_chain.py). Sharp scaling = three-tier structure (Problem 12), heuristic.
3 | A. Foundations | Uniform moment and ergodicity bounds as n → 1 | Bound E[λ^p] and the mixing rate (spectral gap) of the Markov state (S_1, …, S_K) uniformly as n → 1. Start from E[λ] = μ/(1−n) and find how the spectral gap shrinks with ε. Without this, no concentration argument closes. | A lemma with explicit ε-dependence for the moment bounds and for the mixing or contraction rate. | C1, C2 | P1 Core feasibility | Critical | 4 | 3 |  | Done | Draft done 2026-10-24. Key identity A Z = mu - eps*lam for Z=sum(alpha_k/beta_k)S_k. Moments: E Z^p <= C_p eps^-p for all p (induction, constants depend on mu,beta_min,beta_max); sub-exponential tail E exp(eps Z/e) <= 2exp(4mu/(e beta_min)). Contraction in weighted Wasserstein at rate >= eps*beta_min (monotone coupling); slowest mean mode gamma ~ eps/sum(alpha/beta^2), so mixing ~1/(eps*beta), independent of mu. Checked against exact moments and simulation. Needs your re-derivation. Open: true L2 gap, grid-uniform constants, sup over time horizon, non-stationary start. See problem03_moments_mixing.md
4 | A. Foundations | Projection onto Θ_ε | Design a cheap projection, in the Fisher or ONS metric, onto the polytope {μ ≥ μ_min, α ≥ 0, Σ α_k/β_k ≤ 1−ε}. This is an algorithm problem rather than a theory one, but it affects the constants. | An algorithm with O(K) or O(K log K) cost, a note on its effect on the regret constants, and a working implementation. | C1 | P2 Complete upper bound | Medium | 2 | 1 | 1 | Done | 24-25 Oct 2026. problem04_projection.md, code/p4_projection.py. Exact projection onto {mu>=mu_min, alpha>=0, sum alpha_k/beta_k<=1-eps} in a DIAGONAL metric: mu separable; alpha_k = max(0, y_k - tau*w_k/d_k), tau from sorted breakpoints, O(K log K); matches SLSQP on 300 random instances (4e-6); <1 ms for K up to 1e4. Regret-constant effect: non-expansive in the update's own metric, so no extra constant; the cost is cond(D^-1/2 I D^-1/2). K=1: universal ~5.83 (rho^2->1/2), independent of eps (raw ~1e6 at eps=1e-3). K>=2 (corrected 25 Oct after fixing a simulator bug): scaled cond only 1.2-3x below raw and still grows as eps falls (K=2,r=2: 118->368; K=3: 765->2477), so a diagonal metric is NOT enough for K>=2. Open: dense-metric projection (QP, ~O(K^2)), O(K) version, K>=2 preconditioner. Status In progress because 'Done when' asks for the Fisher/ONS metric. UPDATE 25 Oct (problem05_circularity.md): for K=1 the diagonal clip is NOT adequate: it violates non-expansiveness in 0.7-4.6% of steps and inflates regret ~10x when the box is tight (E R_n 16 vs 3.5 at eps=.1; 79 vs 5.4 at eps=.03). Exact F-norm projection onto a box is O(1) for K=1 (edge minimisers + corners) and had 0 violations in 24 configs. Use it. CLOSED 25 Oct (Done): dense F-norm projection for any K (BVLS + bisection on the budget multiplier): matches brute force to 5e-14, non-expansive (0 violations in 2000 pairs), O(K^3) per inner solve (19 ms K=2, 97 ms K=5); the diagonal O(K log K) algorithm remains for the diagonal metric (code/p4_dense_projection.py).
5 | B. Upper bound | Stochastic ONS or recursive-MLE analysis | Prove a regret or excess-risk bound for the Fisher-preconditioned update when data come from the true Hawkes law (or a nearby one). Tools: the score is a martingale difference, Freedman-type concentration, and iterates that are adapted to the path. | A theorem with proof, in expectation or with high probability, under stated assumptions. | C1, C2 | P1 Core feasibility | Critical | 5 | 4 | 1, 3, 4 | Done | 25 Oct 2026. problem05_online_newton.md; code/p5_*.py. First pass, K=1 only. Proposition 1 (rigorous, short): for the unprojected Fisher-scoring/online-Newton update, E<g_i,v_i ¦ past> = E[v_i' dF_i v_i ¦ past] exactly (first-event compensator identity), hence E R_n <= ¦¦th_1-th*¦¦^2_{F_0} + E sum g_i' F_i^-1 g_i, no exp-concavity needed. Checked numerically (pathwise identity to 1e-13; expectation identity within SE; bound ~2x loose). Empirical: regret slope (d/2) in log n; E[R_n - log T_n] ~ flat in eps (-1.2,-2.3,-2.4,-2.8 for eps=.3,.1,.03,.01): no visible +C log(1/eps) in time units; apparent 0.5/eps burn-in cost was the prior term rho0*¦th_1-th*¦^2, vanishes with a weak prior. NOT proven: bound on G (needs leverage bound a'F^-1 a/lam = O(1) and local control, i.e. Problem 7), sharp constant 1/2 (needs localisation), projected algorithm (diag projection not non-expansive in F-norm; unprojected iterates exit Theta_eps in 55-85% of runs), K>=2, high-probability version. Draft, not independently verified. UPDATE 25 Oct: problem05_fisher_concentration.md (K=1, oracle information): Lemma F1 var(int h(S_t)dt) <= 2T Lip sqrt(m) sigma_S/gamma via the Problem-3 contraction; Lemma F2 two-interval bound J_T >= (O/L) Q (exact, deterministic); Theorem F: J_T >= (mT/4L) Q w.p. >=1-2q for all T>=T0=16 sigma_S/(rho gamma m^1.5 q) = O(1/(beta eps)), so Theorem-7 leverage assumptions hold w.h.p. given (L1). Numerics: variance bound holds with 500-1500x margin; pathwise leverage bound 0 violations in ~1300 checks; rigorous T0*gamma ~ 4e5 vs empirical ~20-50 (Chebyshev, 1e4x conservative). OPEN: circularity (L1 needs consistency which needs the information bound), Assumption M (pi-mass of bumps, numerical), exponential tails, projection, K>=2. UPDATE 25 Oct (problem05_circularity.md): circularity avoided by design, not by a consistency bootstrap: compact box Theta_c known a priori + exact F-norm projection => (L1) holds deterministically (c+=max(mu_hi/mu*,al_hi/al*), c-=min(...)); Prop 1 survives projection (non-expansiveness in F-norm); leverage w.h.p. after T0=O(1/(beta eps)) via Theorem F. Numerics (K=1): R_n - log T_n between -4.4 and -0.5 in 24 configs, 0 non-expansiveness violations. Sketched only: stopping-time localisation of the w.h.p. event; burn-in term crude. OPEN: true bootstrap (c->1), K>=2 (QP projection), a priori scale knowledge, exponential tails. UPDATE 25 Oct (problem05_bootstrap.md): TRUE BOOTSTRAP, K=1, two-stage, polynomial tails. Stage 1 with box constants: pathwise D_j <= D0' - X - M + G (M martingale, E m^2 <= (4/c-) E[v'dF v]); Doob L2 + Markov => P(sup D_j >= 3x) <= (1+16/c0-) Gamma/x, Gamma=O(d log T); with F >= lam_T I this forces the iterates into R(delta) for t>=T1 when delta^2 >= 24(1+16/c0-)c0+ L Gamma/(q m lamQ rho*^2 T1) (T1 gamma ~ d log T1/delta^2). Stage 2: with c+-=1+-delta, A->1, B->0, psi-factor 2 -> 1+O(delta): regret (d/2+o(1)) log T on the good event. Numerics: pathwise inequality margin 1e-14; E sum m^2/E X ~4; sup D_j <=14; last exit time from R(delta) ~ 1-3/(delta^2 gamma), slope of E R_n in log T ~0.9 (target d/2=1). NOT proved: expected regret with sharp constant (needs exponential tails; bad event only ~1/T1), localisation bookkeeping, K>=2, a-priori box. UPDATE 25 Oct (problem05_exponential_tails.md): exponential tails. E1 exact identities (eps*Lam_T = mu T + n M'_T - n dS; Poisson eq u=(s-ES)/gamma), verified 1e-14. E2 Lam_T tails exp(-eta^2 mu eps T/2n^2). E3 occupation functionals via Poisson equation + Freedman: P(int h <= Tm/2) <= 3 exp(-c T gamma), c=m^2 mu/(32 kappa^2 (1+eta) beta) ~3e-7 (empirical decay ~0.04-0.056 per unit T*gamma: bound valid but 1e5x pessimistic). E4 Newton martingale: with prob>=1-e^-x, -M_t <= X_t + x/theta for all t (theta=min(1/(2k1), c-/2.87)) so sup D_j <= D0' + x/theta + G_n. Theorem C-exp: bootstrap with T1 = O((ln(1/q)+d log T)/(gamma delta^2)). NOT done: E5 (exp bound on G_n, martingale part of score sum) in detail; expected regret with sharp constant needs episode/restart argument (union bound would pay crude linear rate on [0, T_c ~ log T_n]); constants; K>=2. REASSESSMENT 25 Oct (novelty_reassessment.md): C2's 'C log(1/eps)' should be made explicit: conjecture regret = (d/2) log T + (1/2) log det I(theta*;eps) + O(1) in time units, with (1/2) log det I ~ ((1-k)^+/2) log(1/eps), k=2*mu*m (m=mean lifetime). Exact K=1 slopes confirm the information side (0.40 for k0=0.2); the regret side is DISFAVOURED by a 100-rep test (k0=0.2, E[R - log T] = -3.44+-0.10 at eps=0.3 vs -3.19+-0.32 at eps=0.01, against +1.30 predicted); conjecture withdrawn from the headline. Caveat: the test starts at theta*, so it cannot probe a Bayes/redundancy lower-bound constant. E5 + EXPECTED REGRET 25 Oct (problem05_E5_expected_regret.md, K1_main_results.md): E5 PROVED (Lemmas E5a-d, Prop E5: G_n <= (1+o(1)) logdet + o(1)x + B_X X w.p. >= 1-4e^-x; pathwise inequalities checked, 0 violations in 1.4e6 gaps). Found+fixed a flaw in Theorem 7/Lemma 7c: 'gap leverage <= xbar a.s.' cannot hold (depends on Exp(1) variable); truncation fixes it. Theorem R (K=1): E R_n <= (1/2+O(delta+eta)) d ln T + C, C independent of n, via charging bad events to their own time (no episode union bound); PROVED MODULO Thm F-exp, Assumption M (numerical), known box, and unwritten optional-stopping across random restarts. Rate constants ~1e5 worse than observed. K>=2 open. DEPENDENCIES 25 Oct (K1_completion.md): optional stopping closed (predictable good-gap indicators replace restarts); integrability in Thm F-exp closed; Assumption M closed for eps<=eps_M via the Gamma comparator of Thm T (E_Gamma h = 0.164, 0.044 vs simulated 0.15, 0.05); C(eps)=O(mu d ln(1/(eps delta))/(beta eps^2 delta^2)) (order only). Still assumed: known box; K>=2 open; constants conservative; Thm T itself is a proof outline with numerically verified estimates. ASSUMPTION M certified 25 Oct (thmT_explicit_constants.md): K=1, k0=2, mu=beta=1: m>=0.0248 for eps<=1e-4 (E_Gamma h = 0.164, 0.0444 minus TV<=0.0196). EXTENSIONS 25 Oct (assumptionM_exact.md, box_cost_and_lower_bound.md, K2_regret_chain.md): (1) Assumption M certified by exact Fourier quadrature for K=1, eps<=0.3, k0 in [0.6,4] (m>=0.032); (2) box cost: polynomial in c+,1/c-, empirically ~s^2 at rho0=1 (prior effect), leading constant box-free; scale of mu* not learnable at eps=c/T; (3) K>=2: chain carries over, Assumption M replaced by computable lambda_L (Thm FK), Thm R^(K) (K+1)/2 ln T + C_K, constants uninformative, K=2 slope ~1.3 vs 1.5 [N]; (4) minimax lower bound (d/2)ln n - O(ln ln n) for ANY predictor, conditional on uniformity (U). LaTeX master document: latex/hawkes_master.tex (not compiled). CLOSED 25 Oct (Done): Theorem HP (problem05_07_closure.md): with prob >= 1-6e^-x-P(E^c), R_n <= psi_max(2 i0+3x) + 4[D0' + x/theta + G_n(x)]; plus expected-regret Thm R (sharp constant). Assumptions: known compact convex Theta_c, leverage event, Assumption M (certified K=1) / lambda_L (K>=2). FINAL AUDIT 25 Oct (final_audit.md): fixed constant in Lemma E5c (xbar = lbar m/(c^- mu*), not c^+), replaced loose general-K Lemma E1 by the exact Z_c identity; K=2 pathwise Newton/martingale inequalities verified (code/p5_k2_pathwise_check.py).
6 | B. Upper bound | Make the ε-dependence explicit | Track how the gradient bound, the curvature constant and the burn-in scale with ε and μ. Target form: (d/2) log T + C log(1/ε) + burn-in(με) with d = K+1. Decide what burn-in is really needed (probably of order 1/(με) in time or events). | A theorem statement with every constant written as a function of ε, μ, K and the β-grid. | C2 | P2 Complete upper bound | High | 4 | 3 | 3, 5 | Not started
7 | B. Upper bound | Handle the compensator term | The gradient has the form −a_i/λ_i + b_i. Prove that both parts concentrate jointly with zero mean at θ*, given that b_i is not parallel to a_i. | A lemma bounding the joint deviation of the two gradient components. | C1 | P2 Complete upper bound | High | 3 | 2 | 5 | Done | 25 Oct 2026. problem07_leverage.md; code/p5_leverage.py, p5_theorem_check.py, p5_component_check.py. K=1 only. Split gradient g = s (score at theta*) + h (drift). Lemma 7a (rigorous): E[s¦past]=0, E[s s'¦past]=E[dJ] (stopped martingale). Lemma 7b: E[h'F^-1 h] <= (ell/mu_min) E[v'dF v], ell = sup_u phi'F^-1 phi/lam* (point leverage). Lemma 7c: tr(F^-1 dF) <= r(x) logdet increment, r(x)=x/log(1+x) (gap leverage x). Theorem 7 (conditional on a.s. L1-L3): E R_n <= [P0 + (1+eta) c+ r(x) E logdet(F_n/F_0)]/(1-B), B=(1+1/eta) ell/mu_min<1, closing the gradient-norm term of Problem 5 (growth ~ d log T, constant ~3-6x too big). Leverage scale: worst case is the quiet gap, ell ~ [F^-1]_mumu/mu* ~ (k-1)/(eps T), so B<1 needs ~4(k-1)/(eps^2 mu_min) events: leverage burn-in ~1/eps^2 events (matches Problem 3 mixing; observed medians 1520 at eps=.1, 10086 at eps=.03). Numerics: all three lemmas verified; drift term is negligible in practice (0.02 vs bound 3); full bound valid but 15-40x loose. NOT done: L1-L3 as stopping-time/high-probability statements (needs Fisher concentration, Problems 2-3), projection, K>=2, sharp constant. Draft, not independently verified. UPDATE 25 Oct: problem05_fisher_concentration.md (K=1, oracle information): Lemma F1 var(int h(S_t)dt) <= 2T Lip sqrt(m) sigma_S/gamma via the Problem-3 contraction; Lemma F2 two-interval bound J_T >= (O/L) Q (exact, deterministic); Theorem F: J_T >= (mT/4L) Q w.p. >=1-2q for all T>=T0=16 sigma_S/(rho gamma m^1.5 q) = O(1/(beta eps)), so Theorem-7 leverage assumptions hold w.h.p. given (L1). Numerics: variance bound holds with 500-1500x margin; pathwise leverage bound 0 violations in ~1300 checks; rigorous T0*gamma ~ 4e5 vs empirical ~20-50 (Chebyshev, 1e4x conservative). OPEN: circularity (L1 needs consistency which needs the information bound), Assumption M (pi-mass of bumps, numerical), exponential tails, projection, K>=2. UPDATE 25 Oct: (L1) now holds by construction for the compact-box exact-projection algorithm (problem05_circularity.md); F >= F0 + J/c+ verified PSD in all runs. Remaining: localisation bookkeeping. UPDATE 25 Oct: bootstrap done at polynomial-tail level (problem05_bootstrap.md); remaining for the leverage assumptions: exponential tails, localisation, K>=2. UPDATE 25 Oct: exponential-tail versions of Theorem F and the bootstrap in problem05_exponential_tails.md (G_n control sketched only). CLOSED 25 Oct (Done): Lemma JD (problem05_07_closure.md): joint zero mean and covariance E dJ (non-degenerate since b not parallel to a), pathwise ¦s¦^2_{F^-1} <= (2 lbar/mu)(1+E^2), tail e^-m, cumulative exponential bound (E5b); 0 violations in 1.44e6 gaps.
8 | B. Upper bound | Decide the notion of regret | Log-loss regret against the best fixed θ* is not the same as parameter error. State both, and either prove the link between them or choose one as the headline result. | A precise definition used consistently in all theorems, and a lemma connecting the two notions if both are kept. | C2 | P2 Complete upper bound | Medium | 2 | 1 | 5 | Not started
9 | C. Lower bound and information limits | Two-point lower bound for online estimation | Adapt the kernel-agnostic bound KL ≲ δ² T μ (1−n) to exponential dictionaries, then convert it into a regret or minimax statement. Check that it matches your upper bound in ε. | A lower-bound theorem, and a comparison table showing where upper and lower bounds match or differ in ε, μ and T. | C3 | P3 Lower bound and simulation | High | 4 | 3 | 6, 10 | Not started | LITERATURE 25 Oct: the two-point KL bound is already Herrera-Marin arXiv 2609.38268 Thm 2.2 + Cor 2.3 (empty start, shared mu and kernel shape, any normalised shape incl. sums of exponentials; unrefereed). Re-derived and tested on K=1 (bound held in 12/12 configs, 2-7x loose). Novelty here must come from online-estimator regret or other directions (individual alpha_k, stationary start). REASSESSMENT 25 Oct: as written this problem (two-point bound) is prior art (Herrera-Marin Thm 2.2). Suggested replacement: (a) regret lower bound for sequential estimators >= (d/2) log T + (1/2) log det I - O(1); (b) identifiability map / matching UPPER bound on lambda_min(I) for the K-dictionary. Neither is proved; literature on regret lower bounds for point processes not yet searched.
10 | C. Lower bound and information limits | Fisher information as n → 1 for K = 1 | Compute I(μ, α) for a single exponential with fixed β in closed form, using the stationary law of λ or the CIR scaling limit. This is the quickest test of whether items 9 and 11 are tractable. | Closed-form (or asymptotic) Fisher information, with its behaviour as ε → 0 stated clearly. | C3, C4 | P1 Core feasibility | Critical | 3 | 1.5 |  | Done | Revised 2026-10-25. K=1 near-critical asymptotics of m=E[1/lam] now PROVED (Theorem A: k>1 m~2eps/(2mu-beta); k=1 m~(2/beta)eps ln(1/eps); k<1 m~C eps^k). Correction: total information from a cold start is NOT T*I(theta*): mu-information always diverges (rigorous >= ln(1+beta_max T)/(mu beta_max), any K); dichotomy is log vs polynomial divergence (numerics: slope 2.03 for k=2, ~ln^2 T at k=1, T^(1-k) for k<1); bounded only under stationary start. K>=2: MC consistent, no proof. Cold-start coefficients conjectural. Needs your re-derivation. See problem10_fisher_k1.md and problem10_rigorous.md VERIFICATION 25 Oct (verification_thmA_E_F.md): Theorem A re-derived step by step and tested: CORRECT. Step 2 has two inadequate justifications (x>=1.5 boundedness needs convexity of h; 'denominator <= alpha x^2' does not follow from the displayed bounds) - both statements are true (numerically sup 2.07/alpha resp. 0.667) and repairable. Limits confirmed: m/eps = 1.998 (k0=2), m/eps^k0 = 5.93 -> 6.05 (k0=0.6), m/(eps ln 1/eps) = 1.945 -> 2 (k0=1). UPDATE 25 Oct (theoremA_step2_and_stationary_tv.md): Theorem A Step 2 REPAIRED (Lemma 2: D_eps<=2.08/alpha for all s via convexity of h; D_eps>=0.166/alpha for s>=1/alpha, eps<=1/4, via exact factor r<=1/3 and monotone h/x^2). Theorem A now fully justified; constants verified numerically. LITERATURE 25 Oct (literature_search_report.md): my exact K=1 Hawkes Fisher matrix converges (relative diff ~ eps) to the CIR Fisher matrix of Ben Alaya-Kebaier-Tran Thm 2.1 under (a,b)=(beta mu, beta eps), 2 sigma=beta^2; the conjectured cold-start coefficient 2/(beta(2mu-beta)) equals the CIR critical-case information rate of their Cor 2.3(i). So the K=1 information structure is the Hawkes prelimit of classical CIR theory (fixed regimes); no local-to-critical CIR result found.
11 | C. Lower bound and information limits | Light-tailed baseline information dichotomy | Prove when information about μ diverges or stays bounded in the nearly unstable regime 1−n_T ≍ T⁻¹ for exponential kernels. The CIR limit has a Gamma stationary law; the open step is the case where its shape parameter exceeds 1. Hardest and most novel item on the list. | A theorem (or a clear counterexample) giving the dichotomy, with the role of the shape parameter explicit. | C4 | P4 Stretch and validation | High | 5 | 5 | 3, 10 | Done | Draft done 2026-10-25 (needs your re-derivation). DECISION: C4 uses STATIONARY observation, dichotomy = bounded vs divergent. Rigorous: K=1 full dichotomy (Thm A, B); ANY K with k_K=2*mu*sum(alpha/beta^2)/n: E[1/lam]=O(eps) if k_K>1 (Thm E, corrected Lyapunov log W+psi/W^2 with Perron weights) => no consistent mu-estimator (Cor E'); E[1/lam]>=c eps^(k_K+eta) if k_K<1 (Thm F) => alpha-known information diverges. Pathwise check of generator bounds passed. Open: efficient (alpha-unknown) info divergence for K>=2 (numerics eff/m->1), matching upper bound/estimator (MLE is mixed-normal: observed info random, CV~0.5), k_K=1 borderline, cold-start coefficients. See problem11_dichotomy.md LITERATURE 25 Oct: divergence of mu-information for kappa<=1 is Herrera-Marin Remark 4.8 (Fatou); he states the kappa>1 direction is NOT proved. Gamma shape/Feller threshold k=2*beta*mu/alpha^2 confirmed against Jaisson-Rosenbaum Thm 2.2 (shape 2m*mu; tested, autocorrelation exp(-eps*beta*t) also confirmed). REASSESSMENT 25 Oct: divergence half = Herrera-Marin Remark 4.8; he leaves the converse (kappa>1) unproved. Other session's Theorem A (K=1, stationary) claims it with rates (I have NOT verified its proof). Exact slopes of (1/2) log det I vs log(1/eps): 0.347,0.397,0.404,0.403,0.402 -> (1-k0)/2=0.40 for k0=0.2; -> 0 for k0>=2. K=2 dictionary: A_T matches the K=1 value at equal k=2*mu*m (1.29/1.53/1.79 vs 1.26/1.55/1.78): supports threshold 2*mu*sum(w_k/beta_k)=1. Observation model matters (stationary vs empty start). VERIFICATION 25 Oct (verification_thmA_E_F.md): Lemma H re-derived and holds pathwise in 30/30 (parameter,z) cases; Theorems E and F re-derived: CORRECT given Lemma H; E_pi[A f]=0 and the E/F integral inequalities confirmed by stationary MC (16 independent replicates). GAP in the use of E: Corollary E'/Theorem B compare path laws with the SAME initial state; impossibility is rigorous for the experiment where S_0 (pre-sample history) is given, but for a stationary record with unobserved past one also needs KL(pi_theta¦¦pi_theta') = O(1) (Gamma approx 0.003-0.034; not proved) - same step Herrera-Marin I calls open. Also: the empty-start experiment (the actual streaming setting) has mu-information >= ln T for every k, so the 'mu unlearnable' headline is observation-model specific. UPDATE 25 Oct (theoremA_step2_and_stationary_tv.md): initial-state gap closed for K=1, k0>1: TV(Q,Q') <= sqrt(rho u'I_T u/2) + TV(pi,pi') (Lemma R), and TV(pi_theta,pi_theta') <= C¦delta¦ + C eps^min(1,k0-1/2) via exact characteristic function phi=G*Ftilde (Gamma comparator), imaginary-axis bound ¦D_eps(-i tau)¦<=31.5/alpha, monotone ¦phi¦, and TV <= ¦¦.¦¦_H1/(2 sqrt2). Numerics (FFT inversion of exact ch.f.): TV(pi,pi') = 0.026/0.070 for delta=0.1/0.3, flat in eps from 0.1 to 0.003; TV(pi,Gamma) ~ eps. MY PROOF, NOT REVIEWED; constants not explicit; K>=2, k0<=1 not covered. UPDATE 25 Oct (general_K_impossibility.md): impossibility of consistent mu-estimation for the STATIONARY record with unobserved past now proved for ANY K with k_K>1 (Theorem V: TV(Q,Q') <= C delta sqrt(ln(1/delta))), by a route that bypasses TV(pi_theta,pi_theta'): (1) KL of stationary theta-process vs theta'-dynamics started from pi_theta over a window L+T=O(1/gamma) is O(delta^2) via Theorem E; (2) superposition: process from state s = empty-start + ghost immigrants g_s(t); (3) cluster survival q(s)<=C' gamma e^{-gamma s} from the flow Y'=-BY+alpha(1-e^{-¦Y¦}) and zeta'=-gamma zeta - r(¦Y¦) (first-moment bound would lose ln(1/eps)). Verified: flow vs cluster MC (K=1,2), ghost-hit prob decays e^{-gamma L} (K=2 sim). MY PROOF, UNREVIEWED. TV(pi,pi') for K>=2 itself still open. LITERATURE 25 Oct (literature_search_report.md): CIR side: information about the drift constant finite iff a > sigma (Ben Alaya et al. Thm 2.1); MLE defined only for 2a > sigma^2 (Dehtiar et al.); critical case sqrt(log T) rate. Discrete side: all estimation results found are CLSE/OLS; Li 2011: nonzero initial values => CLSE of immigration mean inconsistent; Anne-Lu-Yu-Zhou 2026: OLS intercept inconsistent in local-to-unity affine processes (no Hawkes, no information bound; overlap risk Medium). Herrera-Marin's Wei-Winnicki attribution UNVERIFIED. THM T CONSTANTS 25 Oct (thmT_explicit_constants.md): Theorem T now has an explicit chain: ¦d¦<=19 (true sup 1.143), tail exponent q=k0/(2(1+3/X0))>1/2 (k/(1+r)^2=k0 exactly), certified TV(pi,Gamma)<=Phi/(2 sqrt2); k0=2: 2e-2 (eps=1e-4), 1e-3 (1e-5), 8.6e-5 (1e-6); bound 1e2-1e3 above truth, valid in all tests. Ridge pair: TV<=2.4e-3+0.39 delta (eps<=1e-5, k0=2, delta<=0.3). Phi by floating-point quadrature of hand-proved majorants, not interval arithmetic; KL step evaluated on a grid; informative only for eps<~1e-4. FINAL AUDIT 25 Oct (final_audit.md): the 'no consistent estimator given S0' statements (Thm B, Cor D, Cor E') were stronger than the KL lemma proves: the correct bound is TV(Q) <= TV(pi_theta, pi_theta') + sqrt(rho T u'Iu/2). Rigorous impossibility: K=1 stationary record (Thm T), any K stationary record with unobserved past (Thm V). K>=2 with S0 observed: open.
12 | C. Lower bound and information limits | Degenerate directions for K > 1 | Determine whether the near-singular direction of the Fisher information is n, μ, or a mixture of the α_k across time scales. | A statement identifying the degenerate eigendirection(s) and how they depend on ε and on the grid. | C3, C4 | P3 Lower bound and simulation | Medium | 3 | 2 | 2, 10 | Done | Draft done 2026-10-25 (needs your re-derivation). I(theta*) has three tiers: top ~1/eps along grad_alpha n=(1/beta_k) (pure n-direction, best determined); K-1 middle 'kernel-shape' directions (sum w_k/beta_k=0) of size O(1) set by the beta-grid via the Hawkes-corrected spectral Gram (checked: 0.0667 pred vs 0.0661 MC, K=2); ridge ~ eps/(mu(k-1)) along (1,-eps*alpha/mu) = mean-rate-preserving mu-n trade (E lam=mu/eps fixed, shape fixed). As eps->0 the RIDGE is the degenerate direction; at moderate eps for K>=3 / tight grids a time-scale MIXTURE is smaller (K=3, beta=(1,2,4): until eps~0.007). Rigorous: ridge Rayleigh bound O(eps) (via Thm E), lambda_max>=(mu/eps-2mu)/¦alpha¦^2, K=1. Heuristic/numerical: middle tier, eigenvector convergence. See problem12_degenerate_directions.md REASSESSMENT 25 Oct: Herrera-Marin II (2609.38267) Sec 5 reports numerically an 'almost flat direction' from K~5 when fitting sums of exponentials to a long-memory kernel (slow poles trade mass with the baseline; not proved, misspecified setting). Same mechanism as my Problem 2 for the well-specified dictionary (lambda_min(I) falls ~10x per added exponential at r=2). Only a LOWER bound on lambda_min is proved here (Theorem T); a matching UPPER bound as K or the grid ratio grows would turn the flat direction into a theorem.
13 | D. Drift tracking | Tracking bound with constant step η | Prove E‖θ̂_t − θ*_t‖² ≲ η σ²(ε) + Δ²/η² for a constant-step estimator and drift rate Δ. Check the exponent on η, since it depends on how the drift enters. | A theorem with ε-explicit constants, and a short comparison with Solo (2018) and Hall–Willett (2016). | C5 | P5 Second paper or optional | High | 4 | 3 | 3, 5 | Not started
14 | D. Drift tracking | Choose the drift model | Choose one: smooth drift, piecewise-constant with jumps, or bounded variation. Each gives a different bound. | One drift model chosen and justified, with reasons for excluding the others. | C5 | P5 Second paper or optional | Medium | 1 | 0.5 |  | Done | DECISION 2026-10-25: bounded variation as piecewise-Lipschitz class (Lipschitz rate Delta, <=J jumps of size <=D, box mu_t in [mu,c_mu*mu], eps_t in [eps,c_eps*eps], fixed reference Fisher norm). Target for P13: eta*sigma^2 + Delta^2/eta^2 (response of a time-varying-gain filter, gain eta*mu_t/eps) + J*D^2/(eta*T); sigma^2=r/(2*eff) (K=1 alpha known: mu/(2*eps*m)). Verified numerically (causal sampling): sinusoid, triangle, ramp, random walk, jumps; K=1,2,3 (grids (1,2),(1,4),(1,2,4),(1,3,9)); noise coeff r/(2 eff) within 3-13% in window; linear window eta<=theta_k*mu^2/a, theta_k~0.013-0.03 (k-dependent). Problem 5 recursion verbatim cannot track drift (needs forgetting). RETRACTED c_lag~1.8: extra lag for alpha-unknown is an amplitude effect of the data-driven preconditioner (1.3-1.75x at A=0.2-0.5, ->1 as A->0), absent with fixed preconditioner. Metric equivalence kappa_I: K=1 7-9, K=2 10-11 (mu x1.5), eps-independent. Hall-Willett VERIFIED from LaTeX source (adversarial regret C(1+sum¦¦lam_{t+1}-Phi_t(lam_t)¦¦_2)*sqrt(T): variation measure is a path length relative to known dynamics, norm not squared; no parameter-drift model). Solo (Piggott-Solo ICASSP 2018) NOT read: closed access, no OA copy (needs your library). Open: K>=4, eps<0.4 for K>=2, analytic derivation of the adaptive-preconditioner excess. See problem14_drift_model.md CLEANUP 25 Oct: stale c_lag / amplitude-independence / K=2 bias-ratio statements struck in the note; noise convention (sigma^2=a=r/(2 eff)); path-length bound V^2/(eta T) (factor 1/2 not derived); jump term units. Label clashes resolved in LABELS.md.
15 | D. Drift tracking | Optimal step size and its ε-dependence | Show how criticality shifts the best step size η, and what that implies for practical tuning. | A formula or scaling law for η*(ε, Δ) and a simulation that confirms it. | C5 | P5 Second paper or optional | Medium | 2 | 1 | 13 | Done | Draft done 2026-10-25, CONDITIONAL on Problem 13 (tracking bound not proved; built on measured MSE structure from P14). MSE(eta)=a*eta+B(eta), a=r/(2*eff). Smooth drift fast regime: eta*=(Delta_e^2/a)^(1/3) ~ eps^(4/3)*Delta^(2/3) (k>1), MSE*=1.5*a*eta*; jumps: eta*=D*mu/sqrt(2*a*L_e) ~ eps^(3/2); k<1 exponents 1+k/3, 1+k/2. Window cap eta<=theta*mu^2/a ~ eps^2 binds as eps->0. Tracking beats static estimator only if P*eff*(A*mu)^2 >~ 16 (checked: 8.7 no gain, 22.6 modest, 34.7 gain 26%). alpha unknown shifts eta* down by ~k^(-1/3). Sim (K=1): smooth alpha-known eta_opt 0.00292/0.00179/0.00089 vs predicted 0.00295/0.00193/0.00095 at eps 0.4/0.3/0.2; jumps within 15-27%. Not done: K>=2 eta_opt, eps<0.2, pure power-law regime. See problem15_step_size.md
16 | E. Misspecification | Exact KL pseudo-truth | Characterize θ† for the Hawkes KL (E* ∫ [λ* log(λ*/λ_θ) − (λ* − λ_θ)] dt), not the quadratic surrogate used in prior work, and prove existence and uniqueness. | A theorem on existence and uniqueness of θ†, with the first-order condition written out. | C6 | P5 Second paper or optional | Medium | 4 | 2 |  | Not started
17 | E. Misspecification | Online convergence to θ† | Show the online estimator converges to θ† under misspecification, with the stability constraint n ≤ 1−ε active. | A convergence theorem (almost sure or in probability) with the active-constraint case handled. | C6 | P5 Second paper or optional | Medium | 4 | 3 | 5, 16 | Not started
18 | E. Misspecification | Bias of n(θ†) versus K | For a power-law truth on a geometric β-grid, give an explicit rate for the bias of n(θ†) as K grows. This is a rational-approximation problem for a completely monotone kernel with a branch point. | An explicit rate (or a numerically supported conjecture) for the bias as a function of K and grid ratio. | C6 | P5 Second paper or optional | Low | 4 | 3 | 16 | Not started
19 | F. Validation | Simulation study | Simulate with Ogata thinning using known (μ, α, β). Sweep ε and T and check that regret and error follow the predicted scalings, including the burn-in. | Plots of error and regret versus T for several ε, with fitted slopes compared with theory. | All | P3 Lower bound and simulation | High | 2 | 2 | 5 | Not started
20 | F. Validation | Real-data check | Test on NSE or Bank Nifty tick or order-flow data. Fit the dictionary, report the estimated n, show the effect of misspecification, and show tracking behaviour across regime changes. Needs access to suitable tick data. | A figure of n̂(t) over a trading period, with a comment on regime shifts and on bias relative to a batch fit. | All | P4 Stretch and validation | Medium | 3 | 3 | 19 | Not started
21 | F. Validation | Baselines to beat | Implement batch MLE, Hall–Willett mirror descent and Solo's fixed-gain estimator, and compare accuracy and per-event cost with your method. | A comparison table of error and runtime on the same simulated and real datasets. | All | P4 Stretch and validation | Medium | 2 | 2 | 19 | Not started
22 | G. Literature | Read the core papers and write 'difference from' statements | Read the papers listed on the Literature sheet in the suggested order and, for each, write one paragraph on how your result differs from theirs. | A related-work section draft with one 'difference from' paragraph per paper. | All | P0 Parallel | High | 2 | 2 |  | Not started
23 | G. Literature | Check the items not verified | Check Zhang 2023 and Wang 2023 online or sequential estimators, online EM for Hawkes (Lemonnier–Vayatis, Zhou–Zha–Song), Bacry–Muzy–Delattre–Hoffmann, and the citation trees of Yang et al. (2017) and Hall–Willett (2016). | A list of anything that anticipates your results, and an update of the overlap-risk column on the Literature sheet. | All | P0 Parallel | Medium | 2 | 1.5 |  | Not started

## Summary
Research problem tracker: summary
All figures below are formulas driven by the Problems sheet. Change Status, Priority or Est. weeks there and this sheet updates.
Overall
Total problems
Total estimated weeks
Weeks completed (Status = Done)
Percent complete (weighted by weeks)
Critical-priority problems still open
Status | Problems | Est. weeks
Not started
In progress
Blocked
Done
Total
Section | Problems | Est. weeks | Done
A. Foundations
B. Upper bound
C. Lower bound and information limits
D. Drift tracking
E. Misspecification
F. Validation
G. Literature
Total
Priority | Problems | Est. weeks | Done
Critical
High
Medium
Low
Estimates of difficulty, priority and weeks are my judgement for a single researcher working sequentially, not measured data. Edit them on the Problems sheet. Weeks are summed, so the total is not a critical-path estimate.

## Roadmap
Suggested order of work
Phase totals pull from the Problems sheet. Item lists show the suggested working order inside each phase.
Phase | What this phase is for | Suggested order (IDs) | Problems | Est. weeks | Done
P0 Parallel | Literature work, run alongside everything else. | 22, 23
P1 Core feasibility | Order: 10, then 1, then 3, then 5. If K = 1 Fisher information is tractable and the stochastic analysis closes, you have the core of a paper. | 10, 1, 3, 5
P2 Complete upper bound | Finish the upper bound with explicit ε-dependence. | 7, 8, 6, 2, 4
P3 Lower bound and simulation | Add the matching lower bound and confirm scalings by simulation. | 9, 12, 19
P4 Stretch and validation | Item 11 is the stretch goal that makes the paper strong. Add baselines and real data. | 11, 21, 20
P5 Second paper or optional | Drift tracking and misspecification. Drop to a second paper if time runs short. | 13, 14, 15, 16, 17, 18
Total
Working order, with titles pulled from the Problems sheet
Step | ID | Problem | Priority | Est. weeks | Status
1 | 10
2 | 1
3 | 3
4 | 5
5 | 7
6 | 8
7 | 6
8 | 2
9 | 4
10 | 9
11 | 12
12 | 19
13 | 11
14 | 21
15 | 20
16 | 13
17 | 14
18 | 15
19 | 16
20 | 17
21 | 18
22 | 22
23 | 23

## Literature
Read order | Paper | Authors / venue | Link or id | Relevant to problem IDs | What to extract | Overlap risk | Read status
1 | Learning the exogenous rate but not the distance to criticality in nearly unstable heavy-tailed Hawkes processes | Herrera-Marín, arXiv, Sept 2026 (unrefereed) | arXiv 2609.38268 | 9, 10, 11, 12 | Theorem 2.2 (kernel-agnostic KL bound), Theorem 4.1, Remark 4.8 (the half-open Feller-type dichotomy). | High | Read 25 Oct 2026 (full text). Thm 2.2, Cor 2.3, Thm 4.1, Rem 4.8 re-derived and tested numerically; overlap with C3 and the kappa<=1 half of C4 confirmed. See literature_crosscheck.md.
2 | Minimax and adaptive inference for branching ratios under long memory | Herrera-Marín, arXiv, Sept 2026 (unrefereed) | arXiv 2609.38267 | 16, 17, 18 | Section 5: pseudo-true branching ratio for sums of K exponentials, quadratic surrogate, flat directions. | High | Partly read 25 Oct 2026 (abstract, Sec 5, Sec 6.2 only). Thm 3.1 and its proof NOT checked.
3 | Tracking Dynamic Point Processes on Networks | Hall and Willett, IEEE Trans. Inf. Theory 62(7), 2016 | arXiv 1409.0031 | 5, 13, 21 | Dynamic mirror descent setup, √T tracking regret and its assumptions. | Medium | Partly read 25 Oct 2026 (Thm 1 statement, Appendix C parametrisation). Proof NOT checked.
4 | Online Learning for Multivariate Hawkes Processes | Yang, Etesami, He, Kiyavash, NeurIPS 2017 | proceedings.neurips.cc (2017, paper 92a0e7a4…) | 5, 6, 21 | How log T is obtained (Tikhonov regularization, discretization, truncation) and what that costs. | Medium | Not read (the arXiv version in the next row was read instead).
5 | Nonparametric Hawkes Processes: Online Estimation and Generalization Bounds | Yang, Etesami, He, Kiyavash, arXiv | arXiv 1801.08273 | 5, 6 | Journal-version regret and stability claims; marked extension. | Medium | Read 25 Oct 2026 (assumptions, eq. (8)-(9), Thm 2, Cor 1). Proof of Thm 2 only skimmed. See literature_crosscheck.md.
6 | Non-Negative Online Estimation for Hawkes Process Networks | Piggott and Solo, ICASSP 2018, pp. 6333-6337 (listed earlier as "Solo") | IEEE Xplore 8462138 | 13, 15, 21 | Fixed-gain recursive estimator on an exponential-type basis; closest prior art for constant step size. | High | Reading: abstract read 25 Oct 2026 (via OpenAlex); full text NOT obtained. Fixed-gain exponentially weighted least squares on a Laguerre basis, non-negativity preserving, two time scales, simulations; abstract states no regret bound or near-critical analysis. See literature_search_report.md.
7 | Hawkes Identification with a Prescribed Causal Basis | Rong and Nair, arXiv, Feb 2026 | arXiv 2602.20795 | 16, 17 | Pseudo-true parameters and CLTs under misspecification (least squares, batch). | Medium | Not started
8 | A non-local estimator for locally stationary Hawkes processes | Deschatre, Gruet, Lotz, arXiv, June 2025 | arXiv 2506.02631 | 13, 14 | Batch MLE theory for time-varying baseline and reproduction rate. | Medium | Not started
9 | Limit theorems for nearly unstable Hawkes processes | Jaisson and Rosenbaum, Ann. Appl. Probab. 25(2), 2015 | arXiv 1310.2033 | 10, 11 | Integrated-CIR scaling limit when T(1−a_T) → λ; the starting point for the information analysis. | Low | Read 25 Oct 2026 (assumptions, Prop 2.1-2.2, Thm 2.2, heuristic derivation); tested against exact K=1 Hawkes. Proof NOT checked.
10 | Logarithmic regret algorithms for online convex optimization | Hazan, Agarwal, Kale, Machine Learning 69, 2007 | ONS reference | 5, 6 | ONS analysis and where exp-concavity is used, to see exactly what must be replaced. | Low | Original returned HTTP 403. Read Hazan's monograph arXiv 1909.05207 Sec 4.2/4.4 instead (criterion, Thm 4.5 statement); proof not re-derived.
11 | Functional limit theorems for Hawkes processes | Horst and Xu, arXiv, 2024 | arXiv 2401.11495 | 10, 11 | Critical Hawkes processes behave like CIR without mean reversion. | Low | Not started
12 | Change Point Detection and Mean-Field Dynamics of Variable Productivity Hawkes Processes | Kresin, Baeumer, Phillips, arXiv, Dec 2025 | arXiv 2512.20068 | 13, 14 | Post-change boundary-layer Fisher information; ingredient for the variance term in tracking. | Medium | Not started
13 | Markov approximation for controlled Hawkes jump-diffusions with general kernels | Khabou and Talbi, arXiv, July 2025 | arXiv 2507.11294 | 16, 17, 18 | Sums of exponentials as universal approximators; no statistics or K-rates. | Low | Not started
14 | Critical reflexivity in financial markets: a Hawkes process analysis | Hardiman, Bercot, Bouchaud, arXiv | arXiv 1302.1405 | 18, 20 | Empirical bias of exponential fits to a power-law process. | Low | Not started
15 | The limits of statistical significance of Hawkes processes fitted to financial data | Lallouache and Challet, Quantitative Finance 16(1), 2016 | arXiv 1406.3967 | 18, 20 | How many exponentials real data supports; O(N) recursion for the likelihood. | Low | Not started
16 | Local asymptotic properties for Cox-Ingersoll-Ross process with discrete observations | Ben Alaya, Kebaier, Tran, Scand. J. Stat. 47(4), 2020 (arXiv 1708.07070v5) | arXiv 1708.07070 | 11 | Tools for transferring CIR estimation theory to the Hawkes setting. | Low | Reading: intro, Thm 2.1, Cor 2.3 read 25 Oct 2026; proofs NOT read. Fixed sub/critical/supercritical regimes only; no local-to-critical (b=c/T) case. Thm 2.1 information matrix and Cor 2.3(i) critical coefficient match my K=1 Hawkes Fisher matrix and cold-start coefficient as eps->0 (lit_check_cir_fisher.py).
17 | Apparent criticality and calibration issues in the Hawkes self-excited point process model | Filimonov and Sornette, arXiv | arXiv 1308.6756 | 20 | Regime shifts produce spurious n ≈ 1; relevant to real-data interpretation. | Low | Not started
18 | Sequential Change-Point Detection for Mutually Exciting Point Processes | arXiv | arXiv 2102.05724 | 14 | CUSUM-type detection; pre-change parameters from batch MLE. | Low | Not started
- | Zhang et al. 2023 online estimator; Wang et al. 2023 sequential estimator | To check | Search needed | 23 | Not verified. Could anticipate parts of the proposal. | Unknown | Not started
- | Online EM for Hawkes (Lemonnier and Vayatis; Zhou, Zha, Song) | To check | Search needed | 23 | Not verified. | Unknown | Not started
- | Bacry, Muzy, Delattre, Hoffmann; Cartea, Cohen, Labyad (arXiv 2111.10637) | To check | Search needed | 23 | Not verified; SGD for Hawkes least-squares contrast. | Unknown | Not started
- | Citation trees of Yang et al. (2017) and Hall–Willett (2016) | To check | Google Scholar | 23 | Look for exponential-dictionary online estimation papers. | Unknown | Not started
19 | Two methods of estimation of the drift parameters of the Cox-Ingersoll-Ross process: continuous observations | Dehtiar, Mishura, Ralchenko, arXiv, May 2020 | arXiv 2005.05262 | 10, 11 | MLE of (a,b) defined only for 2a > sigma^2; stationary Gamma law of shape 2a/sigma^2; MLE formula uses int dr/r and int dt/r (denominator int r * int 1/r - T^2 mirrors det I_T). | Medium | Reading: abstract, Prop 1 and Section 3 read 25 Oct 2026; proofs and the alternative estimator not read.
20 | Near-Unit-Root Theory for Affine Processes | Anne, Lu, Yu, Zhou, arXiv, 27 May 2026 | arXiv 2605.27859 | 10, 11, 18 | CIR limit of local-to-unity discrete-time affine processes with a Feller remark (2mu >= sigma^2); OLS intercept inconsistent in the local-to-unity regime. No Hawkes (0 hits), OLS only, no likelihood information or lower bound. | Medium | Reading: abstract, introduction, Thm 1 discussion and parts of Thm 3-4 read 25 Oct 2026 (71 pages, mostly unread).
21 | Asymptotics of nearly critical Galton-Watson processes with immigration | Kevei, Acta Sci. Math. (Szeged) 77 (2011) 681-702 | arXiv 1107.2440 | 11 | Limit laws: Poisson/compound Poisson when offspring second factorial moment / (1-rho_n) -> 0, negative binomial (discrete Gamma) when it is of the same order. Distribution only, no estimation. | Low | Reading: abstract, introduction, Sections 2.1-2.2 discussion read 25 Oct 2026; proofs not read.
22 | A fluctuation limit theorem of branching processes with immigration and statistical applications | Ma, arXiv, 2009 | arXiv 0906.2586 | 11 | Survey of the CLSE literature for nearly critical GWI (Sriram 1994: branching-diffusion limit for positive variance; Ispany et al. 2005: n^{3/2} normal for vanishing variance); Thm 3.2: CLSE of (m_n, omega_n). | Low | Reading: abstract, introduction, Thm 3.2 read 25 Oct 2026; proofs not read.
23 | Discrete CLSE papers (abstracts only): Wei-Winnicki 1990; Ispany-Pap-van Zuijlen 2005; Li 2011 | Ann. Statist. 18 (1990); Adv. Appl. Probab. 37 (2005); Commun. Statist. Theory Methods (2011) | DOI 10.1214/aos/1176347876; 10.1017/s000186780000029x; 10.1080/03610926.2010.500109 | 11 | Li 2011: with non-zero initial values the CLSE of the immigration mean is not consistent (nearly critical Jirina). Wei-Winnicki abstract states only the aim; Herrera-Marin I attributes to them inconsistency of an immigration-mean estimator in the critical case: UNVERIFIED and in conflict with another summary. | Low | Reading: abstracts only (OpenAlex), 25 Oct 2026. Full texts not obtained.
24 | Regret / redundancy lower bounds: Rissanen 1984 (IEEE IT 30), Rissanen 1986 (Ann. Statist. 14), Merhav-Feder 1998 (IEEE IT 44) | Rissanen; Merhav and Feder | DOI 10.1109/TIT.1984.1056936; 10.1214/aos/1176350051; 10.1109/18.720534 | 9, 5, 6 | Classical (d/2) log n-type lower bounds are for fixed parameters; no Hawkes- or point-process-specific minimax regret lower bound found; none for a triangular array with eps -> 0. | Unknown | Reading: abstracts only; Merhav-Feder PDF host failed TLS verification (not bypassed). Hypotheses of the Rissanen theorems not checked.
Details come from my research summary of 24 Oct 2026. Re-check every claim against the primary source before citing. Herrera-Marín papers are unrefereed arXiv preprints. Overlap risk is my judgement. Updated 25 Oct 2026: rows 7 and 17 corrected, rows 24-29 added from literature_search_report.md; most new entries were read only in part (see Read status).

## Topic
Research topic statement
Working title | Online estimation of near-critical linear Hawkes processes with an exponential dictionary: regret, information limits and tracking as a function of the distance to criticality
Model | λ_t(θ) = μ + Σ_k α_k S_k(t), dS_k = −β_k S_k dt + dN_t, n(θ) = Σ_k α_k/β_k, with a fixed grid β_1 < … < β_K.
Problem | Events arrive as a stream. The state (S_1, …, S_K) is exact and has O(K) size, with no truncation window. The goal is an estimator θ̂_i, updated per event, that is statistically sound even when the true branching ratio n is close to 1, which is where real financial order-flow fits land.
Gap | Online Hawkes estimators exist (Hall–Willett, Yang et al., Solo), but their guarantees hide the dependence on ε = 1 − n inside constants. They are discretized or truncated, and none comes with a lower bound. Near-critical information limits are known for heavy-tailed kernels, but the light-tailed exponential case is open as a theorem.
One-sentence version | We give the first estimator-level theory, with matching upper and lower bounds, for streaming estimation of light-tailed Hawkes processes as the branching ratio approaches 1.
Proposed contributions
C1: Curvature and algorithm | Show that the per-event loss is convex in (μ, α) but not exp-concave, because its Hessian has rank one. Replace the adversarial ONS claim with a stochastic analysis, using Fisher-preconditioned online Newton or recursive MLE on Θ_ε with martingale concentration.
C2: ε-explicit upper bound | Prove regret or estimation error of the form (d/2) log T + C log(1/ε) + burn-in(με), with d = K + 1.
C3: Matching lower bound | A two-point argument based on KL ≲ δ² T μ (1−n), showing which directions are unlearnable when T μ (1−n) = O(1).
C4: Light-tailed information dichotomy | Establish when baseline information diverges or stays bounded in the nearly unstable exponential regime (1−n_T ≍ T⁻¹), via the CIR scaling limit.
C5: Tracking under drift | A bound of the form E‖θ̂_t − θ*_t‖² ≲ η σ²(ε) + Δ²/η² for constant step size η and drift rate Δ.
C6: Misspecification (corollary) | Convergence to the KL pseudo-true parameter θ† when the true kernel is a power law, and the bias of n(θ†) as K grows.
Everything described as 'prove' is a target, not a result. C1 and C2 depend on a curvature argument that you should re-derive yourself; C4 depends on a conjecture that has not been verified.

## Legend
How to use this workbook
Blue text | Cells you are meant to edit: Priority, Difficulty, Est. weeks, Status, Notes on the Problems sheet; Read status on the Literature sheet; the ID column in the Roadmap working order.
Black text | Fixed content (problem descriptions, criteria for being done).
Green text | Formulas that read from another sheet (Summary and Roadmap).
Status | Not started, In progress, Blocked, Done. Pick from the dropdown; Summary and Roadmap update automatically.
Est. weeks | My rough guess for one researcher working on that item alone. It is an assumption, not data. Overwrite with your own numbers.
Difficulty | 1 (routine) to 5 (open research problem). My judgement.
Priority | Critical = decides whether the paper exists; High = needed for the main theorems; Medium = needed for completeness; Low = optional or second paper.
Contribution | C1 to C6 refer to the contributions listed on the Topic sheet.
Depends on | Problem IDs that should be finished, or at least understood, before this one.